## Budget to Actual
McLENNAN COMMUNITY COLLEGE
CAPITAL IMPOVEMENT FUND - BUDGET TO ACTUAL AS OF 2/28/2022
|  | 2021-22 | 2021-22 | 2021-22 | 2021-22 | 2021-22
|  | Revised Budget | Actuals | Encumbrances | Total | Remaining
| Balance of CIF at 9/1/2021 | 973938 | 973938 |  | 973938
Transfers | Transfer from General Fund | 750000 |  |  | 750000
| Transfer from Excess Pledged Revenues | 1000000 |  |  | 1000000
| Total Transfers | 1750000 |  |  | 1750000
Renovations | Highlander Ranch | 25000 |  |  |  | 25000
Construction | CSC Module E Flooring and Restroom | 402000 | 13634 | 388366 | 402000
| LTC Learning Commons (Phase 2) | 513137 | 527469 | 18541 | 546010 | -32873
| BT Building Renovation (Revenue Bond Payment) | 593400 | 116700 | 476700 | 593400
Plant | Replace Cooling Tower Pumps | 267384 |  | 267384 | 267384
Infrastructure | BPAC Plaza Replacement | 313320 | 198573 | 116587 | 315160 | -1840
| BPAC Stage Rigging Repairs | 478000 |  | 478000 | 478000
| MTA Electrical Upgrade | 43619 | 43008 |  | 43008 | 611
Capital | Professional Fees | 50000 | 19152 | 13430 | 32582 | 17418
Contingency | Contingency | 38078 | 848 |  | 848 | 37230
| Total Expenditures | 2723938 | 919384 | 1759008 | 2678392 | 45546
| Net Income | -973938 | -919384 |  | -928392
| Balance of CIF at 2/28/2022 |  | 54554 |  | 45546
| Balance of CIF Reserve Account at 2/28/2022 |  | 3027386