## Budget to Actual
McLENNAN COMMUNITY COLLEGE
CAPITAL IMPOVEMENT FUND - BUDGET TO ACTUAL AS OF 5/31/2022
|  | 2021-22 | 2021-22 | 2021-22 | 2021-22 | 2021-22
|  | Revised Budget | Actuals | Encumbrances | Total | Remaining
| Balance of CIF at 9/1/2021 | 973938 | 973938 |  | 973938
Transfers | Transfer from General Fund | 750000 |  |  | 750000
| Transfer from Excess Pledged Revenues | 1000000 |  |  | 1000000
| Total Transfers | 1750000 |  |  | 1750000
Renovations | Highlander Ranch | 25000 | 6219 | 23809 | 30028 | -5028
Construction | CSC Module E Flooring and Restroom | 402000 | 392016 | 20196 | 412212 | -10212
| LTC Learning Commons (Phase 2) | 513137 | 568204 |  | 568204 | -55067
| BT Building Renovation (Revenue Bond Payment) | 593400 | 593400 |  | 593400
| Cameron House Renovation |  | 34340 |  | 34340 | -34340
Plant | Replace Cooling Tower Pumps | 267384 | 189632 |  | 189632 | 77752
Infrastructure | BPAC Plaza Replacement | 313320 | 297371 | 15554 | 312925 | 395
| BPAC Stage Rigging Repairs | 478000 |  | 478000 | 478000
| MTA Electrical Upgrade | 43619 | 43008 |  | 43008 | 611
Capital | Professional Fees | 50000 | 31807 | 1490 | 33297 | 16703
Contingency | Contingency | 38078 | 14789 |  | 14789 | 23289
| Total Expenditures | 2723938 | 2170786 | 539049 | 2709835 | 14103
| Net Income | -973938 | -2170786 |  | -959835
| Balance of CIF at 5/31/2022 |  | -1196848 |  | 14103
| Balance of CIF Reserve Account at 5/31/2022 |  | 3069593