## Budget to Actual
McLENNAN COMMUNITY COLLEGE
CAPITAL IMPOVEMENT FUND - BUDGET TO ACTUAL AS OF 5/31/2025
|  | 2024-25 | 2024-25 | 2024-25 | 2024-25 | 2024-25
|  | Budget | Actuals | Encumbrances | Total | Remaining
| Balance of CIF at 9/1/2024 | 2227178 | 2227178 |  | 2227178
Transfers | Transfer from General Fund | 750000 |  |  | 0 | 750000
| Transfer from Excess Pledged Revenues | 2800000 |  |  | 0 | 2800000
| Total Income &Transfers | 3550000 | 0 | 0 | 0 | 3550000
Lots & Roads | Sealcoat and restripe parking lots | 50000 |  |  | 0 | 50000
| Highlander Ranch Road Work | 50000 |  |  | 0 | 50000
| Sidewalk Repairs/Replacements | 25000 |  |  | 0 | 25000
Roofs | MTA Roof | 50000 |  |  | 0 | 50000
| MAC Roof Repair | 125000 |  |  | 0 | 125000
| CSC Module F Roof | 800000 | 36000 |  | 36000 | 764000
| Highlander Ranch Roof Replacements | 250000 | 304794 |  | 304794 | -54794
Rental Property | General Repairs | 25000 |  |  | 0 | 25000
Elevators | CSC E and Student Services | 180000 | 78882 |  | 78882 | 101118
Grounds | Highlander Ranch Landscape Improvements | 1000 |  |  | 0 | 1000
ADA & Life | Science Building ADA Entrance | 5000 |  |  | 0 | 5000
Safety Changes
Renovations | Highlander Ranch Maintenance and Fence Repairs | 15000 | 9650 | 1103 | 10753 | 4247
Construction | Cosmetology Renovation | 420000 | 305111 |  | 305111 | 114889
| Highlander Ranch Building Improvements | 90000 | 2250 | 1380 | 3630 | 86370
| Highlander Gym Audio Upgrades | 80000 | 49880 |  | 49880 | 30120
| Highlander Gym Floors - Replacement | 50000 |  |  | 0 | 50000
| Highlander Gym Locker Room Renovation | 250000 |  |  | 0 | 250000
| Cameron Hall Courtyard & Landscaping | 250000 | 11500 |  | 11500 | 238500
| ESEC Flooding Repairs | 36670 | 36669 |  | 36669 | 1
| Tennis Court Resurfacing | 50000 |  |  | 0 | 50000
| Cameron Hall Change Orders | 0 | 66998 | 73175 | 140173 | -140173
| Counseling Center Change Orders | 0 | 42766 |  | 42766 | -42766
| BT Building Renovation (Revenue Bond Payment) | 592400 | 592400 |  | 592400 | 0
Plant | Equipment Replacement | 50000 |  |  | 0 | 50000
Infrastructure | Building Lock Upgrade | 500000 |  | 507986 | 507986 | -7986
| Replace Central Plant Boiler & Enclosure | 600000 | 6500 |  | 6500 | 593500
| BPAC Stage - Sound Clouds | 198030 |  | 192029 | 192029 | 6001
| ESEC HVAC Repairs | 15000 |  |  | 0 | 15000
| Northwood House - AC Replacement | 25000 |  |  | 0 | 25000
| Highlander Ranch Signage | 5000 | 1462 |  | 1462 | 3538
| Highlander Ranch Lighting | 10000 |  |  | 0 | 10000
| Lighting Upgrades in Campus Buildings | 50000 | 27868 | 5114 | 32982 | 17018
| Cameron Hall Technology | 250000 | 34702 | 84507 | 119209 | 130791
Floor Coverings | Floor Covering Replacement | 25000 |  |  | 0 | 25000
Furniture | Cameron Hall Furniture | 100000 |  | 55922 | 55922 | 44078
| Campus Furniture Replacement | 100000 | 34429 | 1277 | 35706 | 64294
Capital | Professional Fees | 60000 | 1500 |  | 1500 | 58500
Contingency | Contingency | 49215 | 25049 |  | 25049 | 24166
| Total Expenditures | 5432315 | 1668410 | 922493 | 2590903 | 2841412
| Net Income | -1882315 | -1668410 |  | -2590903 | 708588
| Balance of CIF at 5/31/2025 | 344863 | 558768 |  | -363725
| Balance of CIF Reserve Account at 5/31/2025 |  | 9041121